## Score
Sl No | Service | Current Issues(Please state the issue clearly) | Attachments(If any) | Expected Outcome
1 | Driving License | No option to upload supporting documents during withdrawal of suspended driving license |  | During Suspension withdrawal, should have option to attach supporting documents | 1 day
2 |  | Due to data migration some drive type are missing in new system so, this need to be updated from database | Screenshot 2025-11-06 at 10.08.46.png | Admin should have add or delete option for drive type | 1 week
3 |  | PDL - Endorsement cum Renewal, less fees payment(Nu. 500) and update issues as well not in print list(renewal transaction no affected) |  | During the endorsement cum renewal of PDL, renewal transaction should have affect and payment should be Nu. 800 not Nu. 500, and the DL should be in print list.
4 |  | PDL has the maximum of 3 years for the license renewal, whereby in case of having to renew more than 3 years if the PDL is not renewed for 3 years, penalty had to be paid double. |  | For PDL renewal for more than 3 years the penalty shouldn't be double.
| Learner License | Cannot view offence detail against learner licence and its getting saved in the system |  |  | 2 days
5 |  | Cannot view the supporting documents uploaded during the issuance of new learner license |  | While uploading the attachment for new learner license should have option to view the attachment | 1 day
6 | Vehicle | The vehicle registration cancellation and ownership transfer can still proceed even when pending offenses against the registered owner exist. |  | If the vehicle have pending offenses all transactions related to that vehicle should be restricted and pop up alert message to be shown | 1 week
7 |  | Due to data migration the status of vehicle does not match the old system, this needs to be updated manually from database | Screenshot 2025-11-06 at 10.23.05.png | Admin should be able to change the status of vehicles, RC status and RWC status | 4 days
8 |  | A client can reserve a vehicle number if not registered already by paying amount, for this the vehicle needs be reserved by updating in the database | NA | Admin users should be able to reserve the requested vehicle number and able to interchange the number and provision to upload the attachment
9 |  | After the client has booked the registration number and during registration to facilitate that number it should be manually swapped from database | NA | Admin should be able to swap the number from frontend by adjusting the registration number sequence and issuing the reserved registration number
10 |  | Taxi and Bus Life Span - Alert message of its useful life span - e.g. This Vehicle has reached its end of Life Span on 2021-07-27 | NA | System should alert owner on the life span during every vehicle transaction and at the end of life span all transactions should be restricted. | 1 week
11 |  | During NOC there is no payment receipt number and date in the letter |  | Should include payment receipt number and date in the letter(attachment) | 1 day
12 |  | Vehicle Ownership Transfer/Renewal - status needs to be changed from database |  | Admin should have option to release and freeze back from outstanding dues. While searching for vehicle should have option to edit status from the results directly.
13 |  | Duplicate Registration of the vehicle - No replacement of the Vehicle Registration Certificate (RC) shall be carried out without physical verification. | Screenshot 2025-11-06 at 10.28.33.png | There should be provision in the remarks to indicate that the vehicle must be brought for physical verification after applying for RC replacement. | 1 week
14 |  | Change in the Vehicle Registration Certificate - A printed copy (one page detail) will be issued in place of RC/Blue Book. | NA | Printable version (include QR Code)/PVC | 4 weeks
15 |  | Vehicle Status - as per court/acc there is need to freeze vehicle transactions | Screenshot 2025-11-06 at 10.23.05.png | There should be new option 'Freezed' in the vehicle status. The function of 'Freezed' is same as that of cancelled and provision to upload the attachment.
16 | Vehicle Ownership Transfer | Users mistakenly update wrong sales deed date, this need to be updated from database | Screenshot 2025-11-06 at 10.34.27.png | Admin should have right to change the date of sale deed, and new owner details | 2 weeks
17 |  | Users mistakenly do ownership transfer to wrong new owner. To rectify this, it needs to be updated from databse
18 | Offence | Users mistakenly update wrong or double offence in Traffic Infringement | Screenshot 2025-11-06 at 10.37.40 AM.png | Admin should be able delete double offence. Admin also should be able to edit offence name and date, and add additional offence, amount should be automatically adjust. The system should not accept the same offence. | 1 week
19 |  | While updating payment, amount should be adjusted from database | NA | While doing payment push in offense the penalty should not be included. It should be same like in payment push of RC and RWC renewal
20 | Pre Departure Inspection(PDI) | While doing PDI, while searching the Driving License, the validity is not shown which leads to selecting expired DL too |  | During the PDI, While searching Driving License, it's validity must be shown | 2 days
21 | Driving Test | Users mistakenly configure double driving test. To delete this it should be done from database | Screenshot 2025-11-06 at 10.41.23.png | Admin should be able to delete driving test configuration upon request | 1 week
22 |  | eTest Theory |  | Module to recheck eTest Theory
23 | Refund | All transactions record should be updated in database when refund to the client is made | NA | Admin should be able to edit all services' payment details for refund case | 3 weeks
24 | Mobile App | New features | NA | Incorporate LL, Emission, PDI&PAI, Offence, LL/DL-Punch/Suspend/Cancel status, Change Mobile Number/Contact Address,QR Code - Scan and Pay etc
25 | All services | While loading the list in dashboard, the loading/populating of data takes too long. | Screenshot 2025-11-06 at 10.44.06.png | The list can load the lateset 100 transaction and while searching it should display the record. In the list the super admin should have option to delete duplicate application | 1 week
26 |  | Block transaction for all services when there is any outstanding due against owner/LL/DL/Vehicle | NA | Block transaction for all services when there is any outstanding due against owner/LL/DL/Vehicle
27 | Automated SMS and email Notification System | The clients overlook RC/RWC/DL Renewal and Offence payment, which leads to penalty. | NA | All transaction have sms/email notifications for all transactions before due date(*** RC, DL) | 1 week
28 | Users | While adding users from the dashboard the user is created successfully, but when the user logins it prompts to reset password again and again. For this the password reset needs to be diabled from database | Screenshot 2025-11-06 at 10.01.42.png | While new users login for the first time with default password, he/she should be able to reset password
29 | Vehicle list in Public | A user can search any vehicle numbers and view details or proceed for transactions, from the public dashboard which leads to privacy concern and mistakenly renew other's vehicle | Screenshot 2025-11-06 at 10.51.42.png | When the public logs in either by NDI or CID with PIN, they can only see their own vehicle details (Vehicle owners and driving license holders only). This to protect any unnecessary access to other private information by searching by all users | many vehicle owner uneducated therefore difficult to restrict renewal
30 | Vehicle | when we do vehicle transaction, there should be provision to show pop up message ownership change |  |  | require more details